## issues
Issue Id | Project | Tags | Summary | Reporter | Created | Updated | Resolved | Priority | Type | State | Assignee | Sprints | Story points | App | Module | Description | Votes
G10-867 | Group 10 |  | Crash when tapping Delete multiple times quickly | zudilovalova | 2025-06-23 12:58 | 2025-06-23 13:06 |  | High | Bug | New | Unassigned | Unscheduled | 0 | Mobile | Tasks | **Environment:** Device: Pixel 7, Pixel 9 pro OS: Android 15, Android 16 ### **Preconditions** There are 3 tasks in the list ### Steps to reproduce 1. Open the Shopping List App 2. Tap the DELETE button quickly multiple times **Actual result:** The app crashes **Expected Result:** The app is stable. The task is deleted ![](crush multitap.mp4){width=70%} | 0
G10-858 | Group 10 |  | It is possible to add 11 Tasks to the list | root | 2025-06-22 21:41 | 2025-06-22 22:46 |  | Low | Bug | New | Unassigned | Unscheduled | 0 | Mobile | Tasks | **Environment:** Device: Pixel 7 OS: Android 16, Android 15 ### Steps to reproduce 1. Open the Shopping List App 2. Input data to the task field Input Data: Any 1-25 letters in Cyrillic symbols 3. Tap the Add button 4. Repeat 2-3 steps 9 times 5. Input data to the task field Input Data: Any 1-25 letters in Cyrillic symbols 6. Tap the Add button **Actual result:** No message, the 11th task is added to the list **Expected Result:** Error message: "You cannot add more than 10 tasks" ![](11 tasks.mp4){width=70%} Qase.io defect: [It is possible to add 11 Tasks to the list](https://app.qase.io/defect/G10/view/556) Found in test run: [Test run 2025/06/22](https://app.qase.io/run/G10/dashboard/108) | 0
G10-859 | Group 10 |  | Some UI elements are displayed in English instead of Russian | root | 2025-06-22 21:50 | 2025-06-22 22:40 |  | High | Bug | New | Unassigned | Unscheduled | 0 | Mobile | Tasks | **Environment:** Device: Pixel 7 OS: Android 16, Android 15 ### Preconditions The device locale is set to Russia. There is a task in the list ### Steps to reproduce *1.* Open the Shopping List App 2\. Verify text fitting and alignment 3\. Check that all text is translated to Russian **Actual result:** Some elements remain in English: "DELETE", "Enter a text" **Expected Result:** All text displayed in Russian ![](Screenshot_20250619_163737.png){width=70%} Qase.io defect: [Some UI elements are displayed in English instead of Russian](https://app.qase.io/defect/G10/view/558) Found in test run: [Test run 2025/06/22](https://app.qase.io/run/G10/dashboard/108) | 0
G10-830 | Group 10 |  | Editing a task allows invalid input | root | 2025-06-19 21:54 | 2025-06-21 16:03 |  | High | Bug | New | Unassigned | Unscheduled | 0 | Mobile | Tasks | **Environment:** Device: Pixel 7 OS: Android 16 ### Preconditions There is a task in the list ### Steps to reproduce 1\. Open the Shopping List App 2\. Long tap on a task 3\. Input data in the task field Input Data: Privet 4\. Tap Confirm **Actual result:** No error message, the task is edited and confirmed **Expected Result:** The user sees the error message ![](invalid data when editing.webm){width=70%} Qase.io defect: [Editing a task allows invalid input](https://app.qase.io/defect/G10/view/541) Found in test run: [Test run 2025/06/19](https://app.qase.io/run/G10/dashboard/104) | 0
G10-829 | Group 10 |  | Valid input is incorrectly rejected (a task with 25 symbols in Cyrillic characters) | root | 2025-06-19 21:39 | 2025-06-21 15:05 |  | Medium | Bug | New | Unassigned | Unscheduled | 0 | Mobile | Tasks | **Environment:** Device: Pixel 7 OS: Android 16 ### **Steps to reproduce** [\#](https://artsiomrusau.youtrack.cloud/issue/G10-827/Space-character-input-is-accepted-as-valid#steps-to-reproduce) 1. Open the Shopping List App 2. Input 25 symbols in Cyrillic characters to the task field 3. Tap the Add button **Actual result:** Error message: "Задача не должна превышать 25 символов" **Expected Result:** The task is added to the list. No error messages ### ![](25 symbols.webm){width=70%} Qase.io defect: [Valid input is incorrectly rejected (a task with 25 symbols in Cyrillic characters)](https://app.qase.io/defect/G10/view/539) | 0
G10-827 | Group 10 |  | Space character input is accepted as valid | root | 2025-06-19 21:28 | 2025-06-21 15:02 |  | Medium | Bug | New | Unassigned | Unscheduled | 0 | Mobile | Tasks | **Environment:** Device: Pixel 7 OS: Android 16 ### Steps to reproduce 1. Open the Shopping List App 2. Input data to the task field Input Data: "space symbol" 3. Tap the Add button **Actual result:** No error message, the task is added to the list **Expected Result:** The user sees the error message ![](Task spaces_1.webm){width=70%} Qase.io defect: [Space character input is accepted as valid](https://app.qase.io/defect/G10/view/540) Found in test run: [Test run 2025/06/19](https://app.qase.io/run/G10/dashboard/104) | 0