## issues
Issue Id | Project | Tags | Summary | Reporter | Created | Updated | Resolved | Priority | Type | State | Assignee | Sprints | Story points | App | Module | Description | Votes
G10-827 | Group 10 |  | Space character input is accepted as valid | root | 2025-06-19 21:28 | 2025-06-23 17:57 |  | Medium | Bug | New | Unassigned | Unscheduled | 0 | Mobile | Tasks | **Environment:** Android Studio Emulator Devices: Pixel 7, Pixel 9 Pro OS: Android 15, Android 16 Model: sdk_gphone64_x86_64 ### Steps to reproduce 1. Open the Shopping List App 2. Input data to the task field Input Data: "space symbol" 3. Tap the Add button **Actual result:** No error message, the task is added to the list **Expected Result:** The user sees the error message ![](Task spaces_1.webm){width=70%} Qase.io defect: [Space character input is accepted as valid](https://app.qase.io/defect/G10/view/540) Found in test run: [Test run 2025/06/19](https://app.qase.io/run/G10/dashboard/104) | 0
G10-829 | Group 10 |  | Valid input is incorrectly rejected (a task with 25 symbols in Cyrillic characters) | root | 2025-06-19 21:39 | 2025-06-23 17:57 |  | Medium | Bug | New | Unassigned | Unscheduled | 0 | Mobile | Tasks | **Environment:** Android Studio Emulator Devices: Pixel 7, Pixel 9 Pro OS: Android 15, Android 16 Model: sdk_gphone64_x86_64 ### **Steps to reproduce** [\#](https://artsiomrusau.youtrack.cloud/issue/G10-827/Space-character-input-is-accepted-as-valid#steps-to-reproduce) 1. Open the Shopping List App 2. Input 25 symbols in Cyrillic characters to the task field 3. Tap the Add button **Actual result:** Error message: "Задача не должна превышать 25 символов" **Expected Result:** The task is added to the list. No error messages ### ![](25 symbols.webm){width=70%} Qase.io defect: [Valid input is incorrectly rejected (a task with 25 symbols in Cyrillic characters)](https://app.qase.io/defect/G10/view/539) | 0
G10-830 | Group 10 |  | Editing a task allows invalid input | root | 2025-06-19 21:54 | 2025-06-23 17:57 |  | High | Bug | New | Unassigned | Unscheduled | 0 | Mobile | Tasks | **Environment:** Android Studio Emulator Devices: Pixel 7, Pixel 9 Pro OS: Android 15, Android 16 Model: sdk_gphone64_x86_64 ### Preconditions There is a task in the list ### Steps to reproduce 1\. Open the Shopping List App 2\. Long tap on a task 3\. Input data in the task field Input Data: Privet 4\. Tap Confirm **Actual result:** No error message, the task is edited and confirmed **Expected Result:** The user sees the error message ![](invalid data when editing.webm){width=70%} Qase.io defect: [Editing a task allows invalid input](https://app.qase.io/defect/G10/view/541) Found in test run: [Test run 2025/06/19](https://app.qase.io/run/G10/dashboard/104) | 0
G10-858 | Group 10 |  | It is possible to add 11 Tasks to the list | root | 2025-06-22 21:41 | 2025-06-23 17:57 |  | Low | Bug | New | Unassigned | Unscheduled | 0 | Mobile | Tasks | **Environment:** Android Studio Emulator Devices: Pixel 7, Pixel 9 Pro OS: Android 15, Android 16 Model: sdk_gphone64_x86_64 ### Steps to reproduce 1. Open the Shopping List App 2. Input data to the task field Input Data: Any 1-25 letters in Cyrillic symbols 3. Tap the Add button 4. Repeat 2-3 steps 9 times 5. Input data to the task field Input Data: Any 1-25 letters in Cyrillic symbols 6. Tap the Add button **Actual result:** No message, the 11th task is added to the list **Expected Result:** Error message: "You cannot add more than 10 tasks" ![](11 tasks.mp4){width=70%} Qase.io defect: [It is possible to add 11 Tasks to the list](https://app.qase.io/defect/G10/view/556) Found in test run: [Test run 2025/06/22](https://app.qase.io/run/G10/dashboard/108) | 0
G10-859 | Group 10 |  | Some UI elements are displayed in English instead of Russian | root | 2025-06-22 21:50 | 2025-06-23 17:57 |  | High | Bug | New | Unassigned | Unscheduled | 0 | Mobile | Tasks | **Environment:** Android Studio Emulator Devices: Pixel 7, Pixel 9 Pro OS: Android 15, Android 16 Model: sdk_gphone64_x86_64 ### Preconditions The device locale is set to Russia. There is a task in the list ### Steps to reproduce *1.* Open the Shopping List App 2\. Verify text fitting and alignment 3\. Check that all text is translated to Russian **Actual result:** Some elements remain in English: "DELETE", "Enter a text" **Expected Result:** All text displayed in Russian ![](Screenshot_20250619_163737.png){width=70%} Qase.io defect: [Some UI elements are displayed in English instead of Russian](https://app.qase.io/defect/G10/view/558) Found in test run: [Test run 2025/06/22](https://app.qase.io/run/G10/dashboard/108) | 0
G10-867 | Group 10 |  | Crash when tapping Delete multiple times quickly | zudilovalova | 2025-06-23 12:58 | 2025-06-23 18:02 |  | High | Bug | New | Unassigned | Unscheduled | 0 | Mobile | Tasks | **Environment:** Android Studio Emulator Devices: Pixel 7, Pixel 9 Pro OS: Android 15, Android 16 Model: sdk_gphone64_x86_64 ### **Preconditions** There are 3 tasks in the list ### Steps to reproduce 1. Open the Shopping List App 2. Tap the DELETE button quickly multiple times **Actual result:** The app crashes **Expected Result:** The app is stable. The task is deleted ![](crush multitap.mp4){width=70%} | 0
G10-874 | Group 10 |  | Input field expands full screen in landscape mode | zudilovalova | 2025-06-23 18:37 | 2025-06-23 18:54 |  | High | Bug | New | Unassigned | Unscheduled | 0 | Mobile | Tasks | **Environment:** Android Studio Emulator Devices: Pixel 7 OS: Android 15 Model: sdk_gphone64_x86_64 ### **Preconditions** There is a task in the list ### Steps to reproduce 1. Open the Shopping List App 2. Rotate the device to landscape orientation 3. Tap on the input field 4. Input valid data in to the input field: привет 5. Tap the Add button **Actual result:** Cannot add a new task in landscape mode — input field expands and the user cannot add a new task **Expected Result:** The task is added ![](Text field bug.mp4){width=70%} | 0